PAINTED MILLWORK

NEW CONSTRUCTION

PaintFactor Specification Doctrine

| Property | Value |
| --- | --- |
| Spec Family ID | SF_MILLWORK_NC_PAINT |
| Version | 1.0.0 |
| Status | DRAFT FOR REVIEW |
| Date Generated | 2026-01-27 |
| Source | NotebookLM Research (44 sources) + PaintFactor Production Rate Reference |

# 1. Scope & Definitions

## 1.1 Millwork Types Covered

| Component | UOM | PaintScope Key | Notes |
| --- | --- | --- | --- |
| Baseboards | LF | PS_SURFACE_LF.TRIM_BASEBOARD | Height: 3.5"-5.5" |
| Door casings | LF | PS_SURFACE_LF.TRIM_CASING_DOOR | Width: 2.25"-3.5" |
| Window casings | LF | PS_SURFACE_LF.TRIM_CASING_WINDOW | Per opening or LF |
| Crown molding | LF | PS_SURFACE_LF.TRIM_CROWN | Width: 4.25"-7.0" |
| Chair rail | LF | PS_SURFACE_LF.TRIM_CHAIR_RAIL | Standard profile |
| Wainscoting | SF | PS_SURFACE_SF.WAINSCOTING | Panel vs beadboard |
| Built-ins | SF+LF | PS_SURFACE_SF.BUILTIN | Hybrid measurement |

## 1.2 Excluded (Separate Spec Families)

| Component | Reason | Target Spec Family |
| --- | --- | --- |
| Interior doors | Different workflow, EA-based | SF_DOOR_NC_PAINT |
| Windows | Glass masking complexity | SF_WINDOW_NC_PAINT |
| Cabinets | Specialized prep workflow | SF_CABINET_REPAINT |
| Exterior millwork | Weathering differences | SF_MILLWORK_EXT_* |

## 1.3 LF to SF Conversion

Formula: SF = LF × (Width in Inches ÷ 12) Per PCA each LF no matter its height is counted as a SF.  So 1LF of .6in base is still counted as 1SF

| Trim Element | Typical Width | SF per 100 LF |
| --- | --- | --- |
| Baseboard | 3.5" - 5.5" | 29 - 46 SF |
| Casing | 2.25" - 3.5" | 18 - 29 SF |
| Crown Molding | 4.25" - 7.0" | 35 - 58 SF |

# 2. Substrate Classification

## 2.1 MDF (Medium Density Fiberboard)

Composition: Sawdust, wood chips, and resin compressed under high pressure

- Uniform surface, no grain pattern or knots

- High face strength, stable dimensionally

- Edges require solvent-based sealer (prevents fiber raise)

- Highly susceptible to moisture if paint film breached

## 2.2 Finger-Joint Pine (FJP)

Composition: Defect-free pine pieces joined with interlocking finger joints

- Visible grain and joints

- Superior nail-holding vs MDF

- Requires stain-blocking primer (resin bleed potential)

- Joint telegraphing possible over time

## 2.3 Factory-Primed vs Field-Primed

| Condition | Additional Prep | Primer Required |
| --- | --- | --- |
| Factory primed (intact) | Light sand, inspect | Often yes - factory primer thin |
| Factory primed (damaged) | Spot prime bare areas | Yes - full coat |
| Unprimed | Full prep per substrate | Yes - seal + build |

# 3. Surface Preparation

## 3.1 Preparation Matrix

| Substrate | Sanding | Filling | Caulking | Priming |
| --- | --- | --- | --- | --- |
| MDF | 120 edges, 220 faces | Nail holes, defects | All joints | Solvent seal + latex build |
| FJP | 150-180 grit | Holes, joint voids | All joints | Stain-blocking |
| Solid wood | 150-180 grit | Nail holes, defects | All joints | Standard primer |
| Composite | Per mfr spec | Minimal | Joints only | Bonding primer if req |

## 3.2 PDCA P14: Levels of Surface Preparation

| Level | Description | Defect Threshold | PF QT Mapping |
| --- | --- | --- | --- |
| Level 1 | Basic | Major defects only | QT2 |
| Level 2 | Standard | Visible defects | QT3 |
| Level 3 | Premium | Minor defects | QT4 |
| Level 4 | Supreme | Any defect > 1/32" | QT5 |

Note: Level 4 required for semi-gloss and gloss finishes - these sheens reveal substrate imperfections.

# 4. Primer Systems

## 4.1 Primer Selection Matrix

| Substrate | Primer Type | Purpose |
| --- | --- | --- |
| MDF (edges) | Solvent-based sealer | Seal edges, prevent fiber raise |
| MDF (faces) | High-build latex | Build film, level surface |
| FJP | Stain-blocking primer | Block resin bleed |
| Solid wood | Standard primer-sealer | Seal, tooth, block stains |
| Factory primed | High-build undercoat | Build film thickness |

## 4.2 Primer Functions

- Seal the substrate - prevent uneven absorption

- Provide tooth - mechanical adhesion for topcoat

- Block stains/tannins - prevent bleed-through

# 5. Finish Coat Systems

## 5.1 Product Categories

| Coating Type | Benefits | Limitations | Recommended Use |
| --- | --- | --- | --- |
| Acrylic Latex | Fast dry, low odor | Lower hardness, fair leveling | QT2-QT3 |
| Waterborne Alkyd | Alkyd-like flow, latex cleanup | Longer dry, technique sensitive | QT4 |
| Waterborne Urethane | Self-leveling, durable | Premium cost | QT4-QT5 |
| Conversion Varnish | Max hardness | 2-part, spray required | QT5-QT6 |

## 5.2 Material System by Quality Tier

| Quality Tier | System ID | Finish Type |
| --- | --- | --- |
| QT2-QT3 | SYS_FF_STANDARD_ACRYLIC | 100% Acrylic enamel |
| QT4 | SYS_FF_MODIFIED_URETHANE | Waterborne alkyd |
| QT5 | SYS_FF_PREMIUM | Premium urethane |
| QT5-QT6 | SYS_FF_GALLERY | Gallery/lacquer system |

## 5.3 Sheen Selection

| Sheen | Minimum QT | Rationale |
| --- | --- | --- |
| Satin | QT3 | Hides minor imperfections |
| Semi-gloss | QT4 | Reveals more; requires better workmanship |
| Gloss | QT5 only | Magnifies every imperfection |

# 6. Quality Tier Matrix

## 6.1 PaintFactor Quality Tier Definitions

| Attribute | QT2 | QT3 | QT4 | QT5 | QT6 |
| --- | --- | --- | --- | --- | --- |
| Prep - Sanding | Rough spots | Light full | 180-220 | 220-320 | 320-400 |
| Prep - Filling | Major defects | Visible | > 1/16" | > 1/32" | All |
| Primer Coats | 1 (factory OK) | 1 full | 1+1 build | 1+2 build | 2+2 build |
| Finish Coats | 1 | 2 | 2 | 2-3 | 3-4 |
| Sand Between | None | If needed | Yes, 220 | Yes, 320 | Yes, 400 |
| Application | Brush/roll or spray | Any | Spray pref | Spray req | HVLP req |
| Inspection Dist | 6 ft | 39" (P1) | 24" | 12" + light | 6" + light |

## 6.2 QT6 Showroom/Museum Grade

QT6 represents work that exceeds standard trade practice:

- Pre-spray inspection with angled light source

- Fill/sand/spot-coat cycle until defect-free

- Controlled environment (dust-free, humidity controlled)

- Gloved handling of finished surfaces

- Lacquer or conversion varnish systems typical

Note: QT6 is economically unstable for most residential. Labor can be 3-4× QT5. Reserve for true showroom applications.

# 7. Productivity Benchmarks

## 7.1 Trim Production Rates

Cross-referenced with PaintFactor Production Rate Reference v1.0

| Task | UOM | QT3 | QT4 | QT5 |
| --- | --- | --- | --- | --- |
| Wipe/dust surfaces | LF/hr | 300 | 300 | 300 |
| Fill fastener holes | LF/hr | 120 | 100 | 80 |
| Caulk joints | LF/hr | 200 | 160 | 120 |
| Sand prep | LF/hr | 200 | 150 | 100 |
| Brush finish coat | LF/hr | 80 | 65 | 50 |
| Spray finish coat | LF/hr | 200 | 160 | 120 |
| Sand between coats | LF/hr | 400 | 250 | 150 |
| Final inspection | LF/hr | 1000 | 600 | 300 |
| Touch-up | LF/hr | 600 | 400 | 250 |

## 7.2 Complexity Modifiers

| Factor | Modifier | Description |
| --- | --- | --- |
| Simple profile | 0.85× | Flat, square-edge trim |
| Standard profile | 1.0× | Typical ogee, cove |
| Complex profile | 1.25× | Multi-piece, built-up crown |
| Ornate profile | 1.40× | Dentil, egg-and-dart |
| Height 8-9' | 1.0× | Standard ladder work |
| Height 9-12' | 1.15× | Step ladder required |
| Height 12'+ | 1.25× | Extension ladder/scaffold |

# 8. Common Defects & Mitigation

| Defect | Cause | Prevention | QT Impact |
| --- | --- | --- | --- |
| Grain raise | Water-based on raw wood/MDF | Solvent seal coat first | All - prevent |
| Telegraphing | FJP joint movement | High-build primer, multiple coats | QT4+ unacceptable |
| Orange peel | Spray technique/viscosity | Proper atomization | QT3 OK, QT4+ no |
| Brush marks | Manual application | Self-leveling enamel, technique | QT2-3 OK, QT4+ spray |
| Sags/runs | Over-application | Proper mil thickness | All - defect |
| Flash | Uneven absorption | Full seal coat, uniform build | QT3+ unacceptable |

# 9. PDCA Standards Reference

PDCA (Painting and Decorating Contractors of America) was formerly known as PCA. Standards retain "P" prefix from original nomenclature.

| Standard | Title | Application |
| --- | --- | --- |
| P1 | Properly Painted Surface | Acceptance criteria - 39" rule |
| P5 | Benchmark Samples | Quality reference samples |
| P7 | Order of Work | Trade coordination sequence |
| P11 | Painter's Caulk | Application requirements |
| P14 | Surface Preparation Levels | Prep intensity definitions |
| P18 | Extra Work | Scope change documentation |
| P24 | Spot Repairs | Touch-up expectations |

## 9.1 PDCA P1 - The 39-Inch Rule

A surface is properly painted when uniform in appearance, free of defects when viewed:

- Without magnification

- At distance of 39 inches (1 meter) or more

- Under finished lighting conditions

- From normal viewing position

Note: P1 applies at QT3. Higher tiers use closer inspection distances.

# 10. Review Checklist

## Sections to Verify

- ☐ Section 1: Scope & Definitions

- ☐ Section 2: Substrates

- ☐ Section 3: Prep Requirements

- ☐ Section 4: Primers

- ☐ Section 5: Finish Coats

- ☐ Section 6: Quality Tiers (including QT6)

- ☐ Section 7: Productivity (cross-referenced)

- ☐ Section 8: Defects

- ☐ Section 9: PDCA Standards

## Cross-References Validated

- ☐ Production rates align with PaintFactor_Production_Rate_Reference.md

- ☐ QT definitions align with Fine_Finish_Doctrine.md

- ☐ Modifier values align with Estimation_Modifiers_Doctrine.md

## Extracted Files

- ☑ Pricing data → millwork_pricing_reference.md

- ☑ Material coverage → millwork_material_coverage_reference.md

Generated by NotebookLM Research Agent | PaintFactor Dev OS v1.0